## Gantt Chart
Bright Coffee Shop Sales Analysis — Gantt Chart
Project period: 22 September 2026 – 11 October 2026 ¦ Submission: 11 October 2026
Task | Start Date | End Date | Duration (days) | Notes | 22 Sep | 23 Sep | 24 Sep | 25 Sep | 26 Sep | 27 Sep | 28 Sep | 29 Sep | 30 Sep | 01 Oct | 02 Oct | 03 Oct | 04 Oct | 05 Oct | 06 Oct | 07 Oct | 08 Oct | 09 Oct | 10 Oct | 11 Oct
Project planning & requirements | 2026-09-22 | 2026-09-22 | 1 | Define objectives and deliverables
Miro planning & architecture | 2026-09-22 | 2026-09-23 | 2 | Map workflow, data sources, and dashboard architecture
Data collection & cleaning | 2026-09-23 | 2026-09-28 | 6 | Review fields, dates, missing values, and data types
SQL analysis in Databricks | 2026-09-28 | 2026-10-02 | 5 | Explore revenue, products, stores, days, and times
Excel pivot tables & charts | 2026-10-02 | 2026-10-05 | 4 | Create pivot charts and validate summaries
Excel dashboard | 2026-10-05 | 2026-10-07 | 3 | Build KPI cards, slicers, and dashboard layout
Power BI dashboard | 2026-10-07 | 2026-10-08 | 2 | Build KPIs, visuals, and filters
Looker Studio dashboard | 2026-10-08 | 2026-10-10 | 3 | Build KPIs, filters, and eight charts
Lovable dashboard | 2026-10-09 | 2026-10-10 | 2 | Create a web dashboard using the analysis
Quality checks & insights | 2026-10-10 | 2026-10-11 | 2 | Validate calculations, filters, charts, and insights
Final presentation & submission | 2026-10-11 | 2026-10-11 | 1 | Prepare findings and submit deliverables